## Product Backlog
Product Name:	RRS
Team ID:

Name:	Brandon Shimanek
Initials:	BJS
Student ID:	1001246560

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	5
Sprint 1 Left	4
Sprint 2 Left	4
Sprint 3 Left	4

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	As a...	I want to...	So that...	Notes
1	1	Complete	1	PM	create robot parts	I can define robot models	No menu required here – run program, create a part
2	2	In-Progress	1	PM	define new robot models	RRS can sell them to our Beloved Customers	Menu needed – create parts, then create a robot model
3	3		1	BC	browse a catalog of robots	I can buy one or more robots	Need to list robots models, then list parts in selected model
4	4		1	SA	create a robot order for a Customer	I can sell robots and thus do my job well	Select robot model and quantity, show details with total price
5	5		1	PB	ensure persistence of the RRS data	we don't lose orders or historical data	Write the data to disk and reload it next time the program runs
6	6		1	PB / SA	view a list of orders per SA	I can estimate the value of employees / I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
7	7			BC	view my orders	see what I have coming to me	Show list of orders for a BC with total price, then list details of selected order
8	8			BC	view my bill	I can pay for my robots	Show a BC invoice. Actual payment is outside the scope of this project
9	9			SA	view a sales report	I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
10	10			PB	view a list of orders	I can manage the company	Show list of every order with total price, then list details of selected order
11	11			SA	create a bulk (2+) robot order for a Customer	avoid proliferation of orders and paperwork	Allow more than one robot model (with respective quantity) on a single order
12	12			PM	hide robot parts	obsolete parts aren't accidentally used	Mark robot parts as “obsolete” and don't allow adding them to new robot models
13	13			PM	hide robot models	obsolete robots aren't ordered	Mark robot models as “obsolete” and don't allow adding them to new orders
14	14			SA	save a draft order and return to it later	I can multi-task between indecisive customers	Save an order that hasn't been complete, and allow SA to resume work on it later
15	15			PM	add custom pictures to robot models	BC are more likely to buy my robots	(Probably can't address until Homework #6)
16	16			BC	see a pie chart of a model's component costs	I can decide if I want a different model	(Probably can't address until Homework #6)
17	17			BC	browse and order robots over the web	I don't have to talk to the Sales Associates!	(Probably can't address until Homework #6)
18	18			PB	avoid any delays in the RRS web software	my SA team is at maximum productivity	This likely means using threads for key processes (Probably can't address until Homework #6)
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint 1 Backlog
Sprint #	1
Start on	9/29/16 12:00 AM
End on	10/6/16 12:00 AM
Demo on

Total Tasks	10
Day 1 Left	9
Day 2 Left	9
Day 3 Left	7
Day 4 Left	5
Day 5 Left	4
Day 6 Left	4
Day 7 Left	3

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	1	Design	Design	Brandon Shimanek	Create Use Case Diagram	Complete
2	1	Design	Design	Brandon Shimanek	Create Use Class Diagram	Complete
3	1	Coding	Coding	Brandon Shimanek	Code Part model object and its derived classes; with tests.	Complete
4	1	Coding	Coding	Brandon Shimanek	Code Part View and Controller	Complete
5	2	Design	Design	Brandon Shimanek	Update Use Case Diagram for Robot creation	Complete
6	2	Design	Design	Brandon Shimanek	Update Class Diagram for robot creation	In-Progress
7	2	Coding	Coding	Brandon Shimanek	Code Robot model object and its derived classes; with tests.	Complete
8	2	Coding	Coding	Brandon Shimanek	Code Robot controller and view	In-Progress
9	2	Design	Design	Brandon Shimanek	Code RRS Manager object that handles menu	In-Progress
10	2	Design	Design	Brandon Shimanek	Code Repository pattern object for robot/part storage with tests.	Complete
Sprint Burn Chart
Days
Tasks

## Sprint NN Backlog
Sprint #					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	23
Day 1 Left	22
Day 2 Left	19
Day 3 Left	15
Day 4 Left	15
Day 5 Left	9
Day 6 Left	4
Day 7 Left	1

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks