## Product Backlog HW 6
Product Name:
Team ID:

Name:	Brandon Shimanek
Initials:	BJS
Student ID:	1001246560

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	12	Status	Sprint Ends
Sprint 1 Left	11	Completed	Oct 06
Sprint 2 Left	9	Completed	Oct 13
Sprint 3 Left	8	Completed	Oct 20
Sprint 4 Left	8	Completed	Oct 27
Sprint 5 Left	7	Completed	Nov 03
Sprint 6 Left	6	Completed	Nov 10
Sprint 7 Left	5	Completed	Nov 17
Sprint 8 Left	3	Due	Nov 22

					Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	Team Size	As a...	I want to...	So that...	Notes
18	1	Completed	5	1	All	open a GUI main window	I can interact with RRS Manager with my mouse	No menu required here – run program, create a part
1	2	Completed	1	1	PM	create robot parts	I can define robot models	No menu required here – run program, create a part
6	3	Completed	5	1	PM	create robot parts via GUI dialogs	I can define robot models	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
2	4	Completed	2	1	PM	define new robot models	RRS can sell them to our Beloved Customers	Menu needed – create parts, then create a robot model
7	5	Completed	6	1	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	Similar to robot parts (perhaps Create > Robot Model)
3	6	Completed	2	1	BC	browse a catalog of robots	I can buy one or more robots	Need to list robots models, then list parts in selected model
8	7	Completed	7	1	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	A text output is OK initially, but an attractive HTML-like output is desired (perhaps (Report > All Robot Models)
9	8	Completed	7	1	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	Add picture when defining robot model, and show it in the robot model report
4	9	Completed	3	1	SA	create a robot order for a Customer	I can sell robots and thus do my job well	Select robot model and quantity, show details with total price
10	10		8	1	PB	Create a new Beloved Customer via GUI	I can keep track of who's buying our products	The usual name, address, phone number, and email address (perhaps Create > Customer)
11	11		8	1	PB	Create a new Sales Associate via GUI	I can keep track of my employees' performance	Name and employee number at a minimum (perhaps Create > Sales Associate)
12	12		8	1	SA	Create a robot order for a Customer via GUI	I can sell robots and thus do my job well
5	13			2	PB	ensure persistence of the RRS data	we don't lose orders or historical data	Write the data to the default filename and reload it next time the program runs
	14			2	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	Write the data to the default filename on command (perhaps File > Save to the default filename)
	15			2	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	Read the data from a user-selected file on command (perhaps File > Open)
	16			2	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	23			2	PB / SA	view a list of orders per SA	I can estimate the value of employees / I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
	24			2	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / I can justify a raise	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	17			3	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	18			3	All	enable copy and paste from text fields	we can save typing	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported

	21			3	BC	view my bill	I can pay for my robots	Show a BC invoice. Actual payment is outside the scope of this project
	22			3	BC	view my bill (invoice) in the GUI	I can pay for my robots	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	25			3	BC	view my orders	see what I have coming to me	Show list of orders for a BC with total price, then list details of selected order
	26			3	BC	view my orders in the GUI	see what I have coming to me	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	27			4	SA	view a sales report	I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
	28			4	SA	view a sales report in the GUI	I can justify a raise	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	19			4	PB	view a list of orders	I can manage the company	Show list of every order with total price, then list details of selected order
	20			4	PB	view a report of all orders in the GUI	I can manage the company	A basic text report is fine (perhaps Report > All Orders)
	29			4	All	Add multi-level undo	Worry less about making mistakes	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	30			4	BC	see a pie chart of a model's component costs	I can decide if I want a different model	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	31			Bonus	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	Allow more than one robot model (with respective quantity) on a single order
	32			Bonus	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	33			Bonus	PM	hide robot models via GUI	obsolete robots aren't ordered	Mark robot models as “obsolete” and don't allow adding them to new orders
	34			Bonus	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	Save an order that hasn't been complete, and allow SA to resume work on it later
	35			Extreme Bonus	BC	browse and order robots over the web	I don't have to talk to the Sales Associates!	(Probably can't address until Homework #6)
	36			Extreme Bonus	PB	avoid any delays in the RRS web software	my SA team is at maximum productivity	This likely means using threads for key processes(Probably can't address until Homework #6)
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Product Backlog HW 5
Product Name:	RRS
Team ID:

Name:	Brandon Shimanek
Initials:	BJS
Student ID:	1001246560

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	5
Sprint 1 Left	4
Sprint 2 Left	2
Sprint 3 Left	1

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	As a...	I want to...	So that...	Notes
1	1	Complete	1	PM	create robot parts	I can define robot models	No menu required here – run program, create a part
2	2	Complete	2	PM	define new robot models	RRS can sell them to our Beloved Customers	Menu needed – create parts, then create a robot model
3	3	Complete	2	BC	browse a catalog of robots	I can buy one or more robots	Need to list robots models, then list parts in selected model
4	4	Complete	3	SA	create a robot order for a Customer	I can sell robots and thus do my job well	Select robot model and quantity, show details with total price
5	5	In-Progress	3	PB	ensure persistence of the RRS data	we don't lose orders or historical data	Write the data to disk and reload it next time the program runs
6	6			PB / SA	view a list of orders per SA	I can estimate the value of employees / I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
7	7			BC	view my orders	see what I have coming to me	Show list of orders for a BC with total price, then list details of selected order
8	8			BC	view my bill	I can pay for my robots	Show a BC invoice. Actual payment is outside the scope of this project
9	9			SA	view a sales report	I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
10	10			PB	view a list of orders	I can manage the company	Show list of every order with total price, then list details of selected order
11	11			SA	create a bulk (2+) robot order for a Customer	avoid proliferation of orders and paperwork	Allow more than one robot model (with respective quantity) on a single order
12	12			PM	hide robot parts	obsolete parts aren't accidentally used	Mark robot parts as “obsolete” and don't allow adding them to new robot models
13	13			PM	hide robot models	obsolete robots aren't ordered	Mark robot models as “obsolete” and don't allow adding them to new orders
14	14			SA	save a draft order and return to it later	I can multi-task between indecisive customers	Save an order that hasn't been complete, and allow SA to resume work on it later
15	15			PM	add custom pictures to robot models	BC are more likely to buy my robots	(Probably can't address until Homework #6)
16	16			BC	see a pie chart of a model's component costs	I can decide if I want a different model	(Probably can't address until Homework #6)
17	17			BC	browse and order robots over the web	I don't have to talk to the Sales Associates!	(Probably can't address until Homework #6)
18	18			PB	avoid any delays in the RRS web software	my SA team is at maximum productivity	This likely means using threads for key processes(Probably can't address until Homework #6)
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 1 Backlog
Sprint #	1
Start on	9/29/16 12:00 AM
End on	10/6/16 12:00 AM
Demo on

Total Tasks	10
Day 1 Left	9
Day 2 Left	9
Day 3 Left	7
Day 4 Left	5
Day 5 Left	4
Day 6 Left	4
Day 7 Left	3

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	1	Design	Design	Brandon Shimanek	Create Use Case Diagram	Complete
2	1	Design	Design	Brandon Shimanek	Create Use Class Diagram	Complete
3	1	Coding	Coding	Brandon Shimanek	Code Part model object and its derived classes; with tests.	Complete
4	1	Coding	Coding	Brandon Shimanek	Code Part View and Controller	Complete
5	2	Design	Design	Brandon Shimanek	Update Use Case Diagram for Robot creation	Complete
6	2	Design	Design	Brandon Shimanek	Update Class Diagram for robot creation	In-Progress
7	2	Coding	Coding	Brandon Shimanek	Code Robot model object and its derived classes; with tests.	Complete
8	2	Coding	Coding	Brandon Shimanek	Code Robot controller and view	In-Progress
9	2	Design	Design	Brandon Shimanek	Code RRS Manager object that handles menu	In-Progress
10	2	Design	Design	Brandon Shimanek	Code Repository pattern object for robot/part storage with tests.	Complete
Sprint Burn Chart
Tasks
Days

## Sprint 2 Backlog
Sprint #	1
Start on	10/6/16 12:00 AM
End on	10/13/16 12:00 AM
Demo on

Total Tasks	8
Day 1 Left	4
Day 2 Left	3
Day 3 Left	3
Day 4 Left	2
Day 5 Left	2
Day 6 Left	1
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
6	2	Design	Design	Brandon Shimanek	Update Class Diagram for robot creation	Complete
8	2	Coding	Coding	Brandon Shimanek	Code Robot controller and view	Complete
9	2	Design	Design	Brandon Shimanek	Code RRS Manager object that handles menu	Complete
10	3	Design	UML	Brandon Shimanek	Update Class Diagram for robot browsing	Complete
11	3	Design	UML	Brandon Shimanek	Update Use Case diagram for robot browsing	Complete
12	3	Coding	Model	Brandon Shimanek	Update Robot model based on new Class diagram	Complete
13	3	Coding	View	Brandon Shimanek	Create new view code based on class diagram	Complete
14	3	Coding	Controller	Brandon Shimanek	Create new controller cose based on class diagram	Complete
Sprint Burn Chart
Tasks
Days

## Sprint 3 Backlog
Sprint #	1
Start on	10/13/16 12:00 AM
End on	10/20/16 12:00 AM
Demo on

Total Tasks	10
Day 1 Left	9
Day 2 Left	7
Day 3 Left	7
Day 4 Left	6
Day 5 Left	5
Day 6 Left	5
Day 7 Left	5

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
15	4	Orders	Design	Brandon Shimanek	Update class diagram for new robot order creation	Complete
16	4	Orders	Design	Brandon Shimanek	Update use case diagram for new robot order creation.	Complete
17	4	Orders	Coding	Brandon Shimanek	Create Robot order model and repo classes.	Complete
18	4	Orders	Coding	Brandon Shimanek	Create Robot order view and controller classes	Complete
19	4	Orders	Coding	Brandon Shimanek	Update menu and add robot order controller to rrs manager class	Complete
20	5	Persistence	Design	Brandon Shimanek	Update class diagram for saving and loading model data	In-progress
21	5	Persistence	Design	Brandon Shimanek	Update use case diagram for data persistence
22	5	Persistence	Coding	Brandon Shimanek	Using tiny xml code for saving data.
23	5	Persistence	Coding	Brandon Shimanek	Using tiny xml code for loading data.
24	5	Persistence	Coding	Brandon Shimanek	Update rrs manager menus and add saving/loading functions.
Sprint Burn Chart
Tasks
Days

## Sprint 4 Backlog
Sprint #
Start on
End on
Demo on

Total Tasks	3
Day 1 Left	3
Day 2 Left	3
Day 3 Left	3
Day 4 Left	3
Day 5 Left	3
Day 6 Left	3
Day 7 Left	3

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
25	18	Generic Gui	Design	Brandon Shimanek	Update Class Diagram for Main gui window	In-progress
26	18	Generic Gui	Design	Brandon Shimanek	Update Use case diagram for main gui window
27	18	Generic Gui	Code	Brandon Shimanek	Code main gui window
Sprint Burn Chart
Tasks
Days

## Sprint 5 Backlog
Sprint #
Start on
End on
Demo on

Total Tasks	6
Day 1 Left	6
Day 2 Left	3
Day 3 Left	3
Day 4 Left	3
Day 5 Left	1
Day 6 Left	1
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	18	GUI	Design	Brandon Shimanek	Update Class diagram for Gui Window	Complete
2	18	GUI	Code	Brandon Shimanek	Create and implement GUI Window in main	Complete
3	6	GUI	Design	Brandon Shimanek	Update Class diagram for Gui Window used in Part creation	Complete
4	6	GUI	Code	Brandon Shimanek	Create Part Creation Window	Complete
5	6	GUI	Code	Brandon Shimanek	Create and setup Proper call backs for part creation window	Complete
6	6	GUI	Code	Brandon Shimanek	Add new utility functions to rrs_io for validating and converting string types to *	Complete
Sprint Burn Chart
Tasks
Days

## Sprint 6 Backlog
Sprint #	6
Start on	11/3/16 12:00 AM
End on	11/10/16 12:00 AM
Demo on

Total Tasks	6
Day 1 Left	6
Day 2 Left	4
Day 3 Left	4
Day 4 Left	2
Day 5 Left	1
Day 6 Left	1
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	7	GUI	Design	Brandon Shimanek	Update Class diagram for Robot model creation	Complete
2	7	GUI	Design	Brandon Shimanek	Updage Uml diagram for Robot model creation	Complete
3	7	GUI	Code	Brandon Shimanek	Create Robot Creation Window	Complete
4	7	GUI	Code	Brandon Shimanek	Update Robot Controller to be called by creation window	Complete
5	7	GUI	Code	Brandon Shimanek	Create Robot Creation Window callbacks	Complete
6	7	GUI	Code	Brandon Shimanek	Hook Robot Creation Window to RrsMainWindow	Complete
Sprint Burn Chart
Tasks
Days

## Sprint 7 Backlog
Sprint #	7
Start on	11/10/16 12:00 AM
End on	11/17/16 12:00 AM
Demo on

Total Tasks	6
Day 1 Left	4
Day 2 Left	2
Day 3 Left	2
Day 4 Left	2
Day 5 Left	2
Day 6 Left	1
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	8	GUI	Design	Brandon Shimanek	Update Class diagram for Robot Browsing	Complete
2	8	GUI	Code	Brandon Shimanek	Create Table/Browser for viewing Robots	Complete
3	8	GUI	Code	Brandon Shimanek	Add Table/Browser for viewing Robots with callback setup.	Complete
4	9	GUI	Design	Brandon Shimanek	Update Class diagram for Robot Model Image	Complete
5	9	GUI	Code	Brandon Shimanek	Add new data item to Robot and update Tests	Complete
6	9	GUI	Code	Brandon Shimanek	Configure callbacks for image display.	Complete
Sprint Burn Chart
Tasks
Days

## Sprint NN Backlog
Sprint #					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	23
Day 1 Left	22
Day 2 Left	19
Day 3 Left	15
Day 4 Left	15
Day 5 Left	9
Day 6 Left	4
Day 7 Left	1

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1
Sprint Burn Chart
Tasks
Days

## 'file:///home/brandon/Downloads/Robbie_Robot_Shop_Scrum.ods'#Product Backlog
36
36
36
36
36
36
36
36
36